###### chapter 2

DECISIONS TO MAKE BEFORE STARTING

This chapter is written for programme directors, their national counterparts, technical resource persons and survey coordinators. It will help you to: ( Identify and contact potential resource persons. ( Decide on the level of aggregation for the estimates. ( Find out how long the survey will take. ( Estimate how much it will cost.

As soon as it is decided that a survey is necessary for measuring the end-decade goals, some important decisions must be made.

- First, identify a survey coordinator and a senior resource person who will be in charge of the design, implementation and analysis of the data.

- Second, decide whether a nationally representative sample is sufficient or whether there is also a need for subnational estimates – for example, at the state or province level.

- Third, establish a timetable for the study. Early planning is crucial because the full survey cycle, from inception to publication of results, may take several months.

- Fourth and finally, calculate how much the survey will cost.

Identifying and Contacting Potential Resource Persons

Do not attempt to do a survey unless you can identify a full-time survey coordinator. There is no substitute for this important person’s role.

A survey coordinator must be identified in collaboration with government partners. This person will preferably be a professional in a governmental institution who is able to dedicate him/herself full-time for the duration of the project (about six months). The coordinator may also be an independent consultant, but should have the respect of national counterparts. Previous experience in survey implementation and a firm grounding in scientific methodology (e.g. a postgraduate degree in public health or a related field) are also required. This person will make sure that the entire process runs smoothly and that the basic protocols are followed, including carrying out the first stages of sampling, selecting and training fieldworkers, supervising overall field activities and processing data. Most importantly, this coordinator will be the person who sees that the survey results are reported in a manner that will help all stakeholders understand their implications and use them for planning and decision making. The survey coordinator will also be responsible for obtaining the assistance of the resource person/s, as well as the cooperation of other government agencies at different levels.

A senior resource person or institution should be identified to collaborate closely with the survey coordinator, especially at the survey design stages. This person will have ample technical expertise in survey design, implementation and analysis. A list of such persons will be available from UNICEF Regional Offices and from the Division of Evaluation, Policy and Planning in New York.

Deciding on the Level of Aggregation of the Indicators

Sample size depends on whether indicators will be measured at the national or subnational level. Countries are expected to fill major gaps in basic indicators so that they may report on end-decade goals at the national level. A typical sample for studying national-level indicators will be around 4,500 households, in around 150 clusters spread across the country (see Chapter 4 for a full discussion of sample size requirements). It will allow estimation of coverage goals with a margin of error of 5 percentage points or less. This will also usually be adequate for providing baseline estimates to compare with data from a repeat survey in several years time, in order to measure changes. Gender-specific estimates will have a margin of error of about 7 percentage points.

Some countries may also wish to have subnational estimates for planning and evaluation purposes. For example, separate estimates for the main provinces or special populations such as slum dwellers may be desirable. Simulations show that samples of 300-500 households per subnational group are sufficient for most end-decade indicators (see Chapter 4). Subgroup estimates, however, will have wider margins of error (10 percentage points) and will be based on broader age groups than required for reporting on goals at the national level. Alternatively, a subgroup could be oversampled, resulting in an increase in the overall number of households to be surveyed. The potential gains from these options need to be carefully weighed against the additional costs in both time and money that they will inevitably entail.

Estimating How Long the Survey Will Take

Due to the pressing need for reporting, survey planning activities should start as soon as possible. Good planning means specifying clearly at the outset what you need to learn from the survey and how you will use that information. Each step should then be tightly orchestrated around those needs, with the report format and plans for dissemination set out in advance. Experience has shown that without such planning, questionnaire length can get out of control with the inclusion of poorly conceived questions that lack a clear purpose. More important, unless the final phase of the survey is planned in detail before the outset, data processing, data analysis and report writing will inevitably be delayed, often to the point of rendering the results obsolete by the time they finally appear.

The model timetable presented in Table 2.1 shows the minimum estimated time for completing the full survey cycle for a sample of 150 clusters of 30 households each. This table is provided for general guidance only, since local characteristics may greatly affect the duration of the study. Important factors include the geography of the country, road conditions and previous experience of the survey team, among others.

##### Table 2.1

##### Typical Timetable for a National Survey Covering 4,500 Households

| Tasks | Weeks |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 |
| Identify resource person and coordinator, plan survey. |  |  |  |  |  |  |  |  |  |  |
| Carry out sampling, adapt and pre-test questionnaire and training materials. |  |  |  |  |  |  |  |  |  |  |
| Complete logistics arrangements. |  |  |  |  |  |  |  |  |  |  |
| Select and train interviewers. |  |  |  |  |  |  |  |  |  |  |
| Conduct pilot study and collect data. |  |  |  |  |  |  |  |  |  |  |
| Enter and clean data. |  |  |  |  |  |  |  |  |  |  |
| Complete data processing. |  |  |  |  |  |  |  |  |  |  |
| Prepare report and disseminate widely. |  |  |  |  |  |  |  |  |  |  |
| Assumptions: 150 clusters of 30 households; one cluster a day with two interviewers. This equals 300 interviewer-days of data collection, or 4 weeks for 20 interviewers allowing travel time and a safety margin. |  |  |  |  |  |  |  |  |  |  |

- Important:

A very important issue which may affect the timing of your survey is seasonality. Fieldwork may not be feasible during the rainy season due to poor road conditions, or during special religious holidays such as Ramadan. Also, some indicators may show seasonal variations, such as the prevalence of malnutrition. These influences must be taken into account, particularly if the survey results will be compared with earlier findings.

Calculating How Much the Survey Will Cost

Costs will vary widely from country to country. This variability depends not only on currency and labour costs, but also on the degree to which one can reduce costs by using existing facilities. For example, you can achieve important savings by using government personnel for interviewing, employing public or government-provided transportation, obtaining free accommodations and meals for the survey team from local institutions, and so forth.

Table 2.2 contains a comprehensive checklist of expenditure items. As discussed above, many of the items may not be applicable for particular countries. When applicable, the expenditure is described for a survey with five teams – each team consisting of four interviewers, a supervisor and a driver – spending four weeks in the field. Three additional weeks, for training and the pilot study, are also budgeted for supervisors and interviewers. Their accommodation costs cover the training period as well as the fieldwork because it is recommended that they be brought to a central location for all training.

UNICEF’s Eastern and Southern Africa Regional Office prepared a comprehensive costing framework to help standardize the process of figuring survey costs. Country offices in the region were advised to use this framework to help make the process of cost-sharing more transparent and the MICS surveys more cost-efficient. The framework incorporates a breakdown of expenditures within each type of activity. It is intended to help national statistical offices identify activities needing donor support, and to be used by donors in deciding how to share costs. If used widely, this framework will also help to provide a comparison of MICS costs across countries.

This framework is shown in Tables 2.3 and 2.4. Using the standard categories provided (which can be expanded if desired), costs can be allocated to each type of activity involved in the survey process.

Table 2.2

Common Survey Budget Items and Approximate Estimates
for a Survey of 4,500 Households

Budget item	Basis for calculation

Personnel (salaries plus indirect costs)

Consultants	variable

Field supervisors	5 supervisors x 8 weeks

Interviewers	20 interviewers x 8 weeks

Drivers	5 drivers x 4 weeks

Translators	variable

Local guides	5 guides x 4 weeks

Data entry clerks	2 clerks x 5 weeks

Computer programmers	1 programmer x 8 weeks

Transportation

Vehicle rental	5 cars x 4 weeks

Public transportation allowance (urban areas)	variable

Fuel	provision for 5 cars x 4 weeks

Contingency costs (repairs, ferries, etc.)	variable

Consultant’s visit	variable

Per diems (room and board)

Field supervisors	5 supervisors x 8 weeks

Interviewers	20 interviewers x 8 weeks

Drivers	5 drivers x 4 weeks

Translators	variable

Local guides (meal allowance) ………….	variable

Consumables

Stationery (paper, pencils, pens, etc.)	variable

Identification cards	variable

Envelopes for filing	120 envelopes

Computing supplies (paper, diskettes, ribbons, cartridges)	variable

Other costs

Questionnaire and form printing	6,000 sets

Photocopies of maps, listings and instruction manuals	100 maps, etc.

Anthropometric equipment (weighing scales, height/length boards, etc.)	24 sets

Communications (phone, fax, postage, etc.)	variable

Report writing and printing	variable

Table 2.3

MICS Costing Framework:

Items Included in Cost and Activity Categories

| Cost categories | Activity categories |
| --- | --- |
| Personnel (salaries) | Preparation/sensitization |
| Consultants | Preparation of questionnaire |
| Field supervisors | Preparation of dummy tables |
| Interviewers/enumerators | Translation and back-translation |
| Drivers | Pre-testing of questionnaire |
| Translators | Publicity before and after enumeration |
| Local guides |  |
| Data entry clerks | Pilot study |
| Computer programmers | Training |
| Overtime payments | Data collection |
| Incentive allowance | Data analysis |
| Coordinating committee | Report on the pilot study |
| Per diem (room and board) | Survey design and sample preparation |
| Field supervisors | Planning |
| Interviewers/enumerators | Sample preparation |
| Drivers |  |
| Translators | Training |
| Local guides (meal allowance) | Preparation of training materials |
| Consultants/monitors | Translation into training language |
|  | Implementation of training |
| Transportation |  |
| Vehicle rental | Main survey implementation |
| Public transportation allowance | Implementation |
| Fuel | Monitoring and supervision |
| Maintenance costs | Data retrieval |
| Consultant visits |  |
|  | Data input |
| Consumables | Data entry |
| Stationery (papers, pencils, pens, etc.) | Error checking |
| Identification cards |  |
| Envelopes for filing | Data processing and analysis |
| Computing supplies (paper, diskettes, ribbons, | Data processing |
| cartridges) | Data cleaning |
|  | Indicator production |
| Equipment | Tables of analysis |
| Anthropometric equipment |  |
| (weighing scales, height/length boards, etc.) | Report writing |
| Other costs | Dissemination and further analysis |
| Printing (questionnaire, etc.) | Report printing |
| Photocopies of maps, listings, instruction manuals | Distribution |
| Equipment maintenance | Feedback meetings |
| Communications (phone, fax, postage, etc.) | Further analysis |
| Report writing and printing |  |

Table 2.4

MICS Costing Framework

| COST CATEGORIES | TOTAL COSTS | ACTIVITY CATEGORIES |
| --- | --- | --- |
|  |  | Preparation/ sensitization | Pilot study | Survey design and sample preparation | Training | Main survey implementation | Data input | Data processing and analysis | Report writing | Dissemination and further analysis |
| Personnel |  |  |  |  |  |  |  |  |  |  |
| Per diem |  |  |  |  |  |  |  |  |  |  |
| Transportation |  |  |  |  |  |  |  |  |  |  |
| Consumables |  |  |  |  |  |  |  |  |  |  |
| Equipment |  |  |  |  |  |  |  |  |  |  |
| Other costs |  |  |  |  |  |  |  |  |  |  |
| TOTAL COSTS |  |  |  |  |  |  |  |  |  |  |
| Implementing agencies (names) |  |  |  |  |  |  |  |  |  |  |

Supplementary details

1.	Sample size:  ________     Number of households in cluster:  ________     Number of clusters:  ________

2.	Number of field enumerators/supervisors     Enumerators:  ________     Supervisors:  ________

3.	Duration of training for enumerators (number of days):  ________

4.	Duration of enumeration (number of days):  ________

- Data entry/key strokes per questionnaire:  ________

- UNICEF contribution:  $  ________________________