Terms of Reference

Qualitative Researcher for Survey Methodology - Consultancy

Location:			Remote Based

Language(s) Required:		English

Travel: 				Yes

Duration of Contract:		12 October 2015 – 29 January 2016 (45 est. working days)

Application Deadline:		21 August 2015

Background & Rationale

UNICEF places a high priority on the availability of recent and reliable information for monitoring the situation of children, young people and families, for developing evidence-based policies and programmes, as well as for assessing countries’ progress toward national goals and global commitments, including the Millennium Development Goals (MDGs).

UNICEF assists countries in collecting and analysing data in order to fill data gaps for monitoring the situation of children and women through its international household survey programme, the Multiple Indicator Cluster Surveys (MICS). MICS enables countries to produce statistically sound and internationally comparable estimates of a range of indicators in the areas of health, nutrition, education, child protection, water and sanitation and HIV and AIDS. For many countries, MICS surveys are among the most important sources of data used for situation analyses, policy decisions and programme interventions, for informing public opinion on the situation of children and women and influencing the public debate. MICS surveys are usually carried out by government organizations, with the support and technical assistance of UNICEF.

MICS is engaged in a programme of active methodological work with the aims of refining existing survey tools, developing new tools and understanding how these work together in MICS surveys. Prior to the start of a new round of MICS, new tools such as questionnaire modules and protocols are validated, field tested and piloted within the MICS framework. MICS is currently in its fifth round and will enter into the sixth round in 2016. In anticipation of MICS6, there will be a number of new questionnaire modules and protocols and a number of refinements to the existing tools. To examine how these new items and refinements function, MICS will implement a field test of instruments in Belize, a country which has extensive experience with MICS. The field test will use a mixed-methods approach to examine the main objectives. The field test will be developed to allow for statistical testing of main research questions. Then, qualitative methods such as cognitive interviewing of respondents, debriefing of interviewers and field staff and behaviour coding can be used to further understand questionnaire and procedural issues that are not covered by the proposed statistical methods.

Purpose

The purpose of this consultancy is to support the qualitative component of the field test of MICS in Belize. The main objectives of the qualitative aspects are to: 1) understand how and if the addition of new protocols affect field work, 2) examine respondent understanding and responses of certain areas of the questionnaire, and 3) examine problems faced during implementation of field work.

In collaboration with the MICS team and based on the key research questions, the consultant is expected to:

- Develop suitable study methods (e.g. cognitive interview, structured observation, focus groups, etc.) and protocols to address the main objectives

- Implement these protocols, alone and/or with additional support from the MICS team and others in the field test

- Propose and develop qualitative analysis for the data collected

- Write a MICS methodological paper with the findings of the exercise

Expected results  (measurable results):

The expected results are recommendations to the MICS programme on questionnaire design and content, through a MICS methodological paper.

Deliverables

| Expected results | Expected deliverable | ESTIMATED # of working days |
| --- | --- | --- |
| Develop research objectives | Statement of research objectives | 2 |
| Devise suitable methods to study the objectives and prepare protocols for the methods | Study protocols with details of field implementation (training, supervision, data analysis, etc.) | 4 |
| Implement protocols during Belize field test (Expected dates: 22 November–12 December) | Report from field work, with details of issues seen in the field and likely impacts on results | 21 |
| Analysis of data from Belize field test | Summary of analytical procedures to be used and draft of results | 8 |
| Finalize MICS Methodological paper on Belize field test (Mid-January 2016) | MICS methodological paper, following the usual scientific format, including Introduction, Methods, Results and Discussion and conclusions | 10 |
| TOTAL |  | 45 Days |

Duty Station

The consultancy is expected to be home based with possible travel to NY.  Travel to Belize for the duration of the field test is essential.

Timeframe

The duration of the assignment is approximately 45 working days.

Start date: 12 October 2015 		End date: 29 January 2016

Key skills, technical background, and experience required

- At least a Master’s degree in anthropology, social sciences, public health or another field with strong qualitative training

- 5-8 years of relevant mid-level professional experience

- Training and experience in survey methodology highly desired

- Familiarity or experience with MICS, other large-scale surveys and development of survey methods and techniques highly desirable

- Strong communication and interpersonal skills

- Demonstrated ability to write scientific work

How to Apply

Applicants are requested to send their submissions to pdconsultants@unicef.org with subject line: “Qualitative Researcher for Survey Methodology – Consultancy” by 21 August 2015,

5:00pm EST.

Applications must include:

- Cover letter,

- CV, and

- P11 form (http://www.unicef.org/about/employ/files/P11.doc)

- Indicate where you heard about this advertisement

Please indicate your ability, availability and daily/monthly rate (in US$) to undertake the terms of reference.  Applications submitted without a daily/monthly rate will not be considered. Joint applications of two or more individuals are not accepted.

NOTE: Files should not exceed 5.0MB limit

UNICEF is committed to achieving workforce diversity in terms of gender, nationality and culture. Individuals from minority groups, indigenous groups and persons with disabilities are equally encouraged to apply. All applications will be treated with the strictest confidence.

General Conditions of Contracts for the Services of Consultants / Individual Contractors

1. Legal Status

The individual engaged by UNICEF under this contract as a consultant or individual contractors (the “Contractor”) is engaged in a personal capacity and not as representatives of a Government or of any other entity external to the United Nations.  The Contractor is neither a "staff member" under the Staff Regulations of the United Nations and UNICEF policies and procedures nor an "official" for the purpose of the Convention on the Privileges and Immunities of the United Nations, 1946.  The Contractor may, however, be afforded the status of "Experts on Mission" in the sense of Section 22 of Article VI of the Convention and the Contractor is required by UNICEF to travel in order to fulfill the requirements of this contract, the Contractor may be issued a United Nations Certificate in accordance with Section 26 of Article VII of the Convention.

2. Obligations

The Contractor shall complete the assignment set out in the Terms of Reference for this contract with due diligence, efficiency and economy, in accordance with generally accepted professional techniques and practices.

The Contractor must respect the impartiality and independence of UNICEF and the United Nations and in connection with this contract must neither seek nor accept instructions from anyone other than UNICEF.  During the term of this contract the Contractor must refrain from any conduct that would adversely reflect on UNICEF or the United Nations and must not engage in any activity that is incompatible with the administrative instructions and policies and procedures of UNICEF.  The Contractor must exercise the utmost discretion in all matters relating to this contract.

In particular, but without limiting the foregoing, the Contractor  (a) will conduct him- or herself in a manner consistent with the Standards of Conduct in the International Civil Service; and (b)  will comply with the administrative instructions and policies and procedures of UNICE relating to fraud and corruption; information disclosure; use of electronic communication assets; harassment, sexual harassment and abuse of authority; and the requirements set forth in the Secretary General's Bulletin on Special Measures for Protection from Sexual Exploitation and Sexual Abuse.

Unless otherwise authorized by the appropriate official in the office concerned, the Contractor must not communicate at any time to the media or to any institution, person, Government or other entity external to UNICEF any information that has not been made public and which has become known to the Contractor by reason of his or her association with UNICEF or the United Nations.  The Contractor may not use such information without the written authorization of UNICEF, and shall under no circumstances use such information for his or her private advantage or that of others. These obligations do not lapse upon termination of this contact.

3. Title rights

UNICEF shall be entitled to all property rights, including but not limited to patents, copyrights and trademarks, with regard to material created by the Contractor which bears a direct relation to, or is made in order to perform, this contract.  At the request of UNICEF, the Contractor shall assist in securing such property rights and transferring them to UNICEF in compliance with the requirements of the law governing such rights.

4. Travel

If UNICEF determines that the Contractor needs to travel in order to perform this contract, that travel shall be specified in the contract and the Contractor’s travel costs shall be set out in the contract, on the following basis:

- UNICEF will pay for travel in economy class via the most direct and economical route; provided however that in exceptional circumstances, such as for medical reasons, travel in business class may be approved by UNICEF on a case-by-case basis.

- UNICEF will reimburse the Contractor for out-of-pocket expenses associated with such travel by paying an amount equivalent to the daily subsistence allowance that would be paid to staff members undertaking similar travel for official purposes.

5. Statement of good health

Before commencing work, the Contractor must deliver to UNICEF a certified self-statement of good health and to take full responsibility for the accuracy of that statement.  In addition, the Contractor must include in this statement of good health (a) confirmation that he or she has been informed regarding inoculations required for him or her to receive, at his or her own cost and from his or her own medical practitioner or other party, for travel to the country or countries to which travel is authorized; and (b) a statement he or she is covered by medical/health insurance and that, if required to travel beyond commuting distance from his or her usual place or residence to UNICEF (other than to duty station(s) with hardship ratings “H” and “A”, a list of which has been provided to the Contractor) the Contractor’s medical/health insurance covers medical evacuations. The Contractor will be responsible for assuming all costs that may be occurred in relation to the statement of good health.

6. Insurance

The Contractor is fully responsible for arranging, at his or her own expense, such life, health and other forms of insurance covering the term of this contract as he or she considers appropriate taking into account, among other things, the requirements of paragraph 5 above.  The Contractor is not eligible to participate in the life or health insurance schemes available to UNICEF and United Nations staff members.  The responsibility of UNICEF and the United Nations is limited solely to the payment of compensation under the conditions described in paragraph 7 below.

7. Service incurred death, injury or illness

If the Contractor is travelling with UNICEF’s prior approval and at UNICEF's expense in order to perform his or her obligations under this contract, or is performing his or her obligations under this contract in a UNICEF or United Nations office with UNICEF’s approval, the Contractor (or his or her dependents as appropriate), shall be entitled to compensation from UNICEF in the event of death, injury or illness attributable to the fact that the Contractor was travelling  with UNICEF’s prior approval and at UNICEF's expense in order to perform his or her obligations under this contractor, or was performing his or her obligations under this contract in a UNICEF or United Nations office with UNICEF’s approval.  Such compensation will be paid through a third party insurance provider retained by UNICEF and shall be capped at the amounts set out in the Administrative Instruction on Individual Consultants and Contractors. Under no circumstances will UNICEF be liable for any other or greater payments to the Contractor (or his or her dependents as appropriate).

8. Arbitration

- Any dispute arising out of or, in connection with, this contract shall be resolved through amicable negotiation between the parties.

- If the parties are not able to reach agreement after attempting amicable negotiation for a period of thirty (30) days after one party has notified the other of such a dispute, either party may submit the matter to arbitration in accordance with the UNCITRAL procedures within fifteen (15) days thereafter.  If neither party submits the matter for arbitration within the specified time the dispute will be deemed resolved to the full satisfaction of both parties.  Such arbitration shall take place in New York before a single arbitrator agreed to by both parties; provided however that should the parties be unable to agree on a single arbitrator within thirty days of the request for arbitration, the arbitrator shall be designated by the United Nations Legal Counsel.  The decision rendered in the arbitration shall constitute final adjudication of the dispute.

9. Penalties for Underperformance

Payment of fees to the Contractor under this contractor, including each installment or periodic payment (if any), is subject to the Contractor’s full and complete performance of his or her obligations under this contract with regard to such payment to UNICEF’s satisfaction, and UNICEF’s certification to that effect.

10. Termination of Contract

This contract may be terminated by either party before its specified termination date by giving notice in writing to the other party.  The period of notice shall be five (5) business days (in the UNICEF office engaging the Contractor) in the case of contracts for a total period of less than two (2) months and ten (10) business days (in the UNICEF office engaging the Contractor)  in the case of contracts for a longer period; provided however that in the event of termination on the grounds of impropriety or other misconduct by the Contractor (including but not limited to breach by the Contractor of relevant UNICEF policies, procedures, and administrative instructions), UNICEF shall be entitled to terminate the contract without notice.  If this contract is terminated in accordance with this paragraph 10, the Contractor shall be paid on a pro rata basis determined by UNICEF for the actual amount of work performed to UNICEF’s satisfaction at the time of termination. UNICEF will also pay any outstanding reimbursement claims related to travel by the Contractor.  Any additional costs incurred by UNICEF resulting from the termination of the contract by either party may be withheld from any amount otherwise due to the Contractor under this paragraph 10.

11. Taxation

UNICEF and the United Nations accept no liability for any taxes, duty or other contribution payable by the consultant and individual contractor on payments made under this contract.  Neither UNICEF nor the United Nations will issue a statement of earnings to the consultant and individual contractor.