**APPENDIX**

to the MEMORANDUM OF UNDERSTANDING

on

TECHNICAL COLLABORATION

between

the NATIONAL STATISTICAL OFFICE and the UNICEF COUNTRY COUNTRY OFFICE

for the execution of the project

"***Multiple Indicator Cluster Survey (MICS) Year***"

**I. Governance and Resources**

1. **Attendance to the Workshop on Survey Design**. Prior to or following the signing of this Memorandum of Understanding, the country survey team, including the UNICEF MICS focal point, the survey coordinator, sampling expert and, if identified, national MICS consultant participate in the Workshop on Survey Design, organized by UNICEF Global MICS Team.

Discussions are held during the workshop with the UNICEF Headquarters (HQ) MICS team, UNICEF Regional MICS Coordinator and UNICEF Regional Office (RO) experts (on Sampling and Household Surveys) on planning for the survey. Using MICS templates, the country survey team works on an initial outline of the Country Survey Plan and Budget and presents at the end of the workshop.

1. **Survey Plan and Budget**. Country Survey Plan and Budget is then drafted at country level, shared with UNICEF RO/HQ for review and then finalized. The regional household survey expert and/or UNICEF RO MICS coordinator may visit the country at this stage to support planning for the MICS. This visit may coincide with the visit of the regional sampling expert (described in II.2).
2. **Identification and Recruitment of Survey Personnel.** Other key technical experts from the NSO are identified and a national MICS consultant is hired. UNICEF RO/HQ support the recruitment of the national MICS consultant (sharing generic Terms of References (ToR) template, names of potential candidates and supporting the selection process).
3. **Survey Committees.** Steering and Technical Committees are established. The Steering Committee is the main body responsible for MICS constituting a forum for a consultative process. The main role of the Technical Committee is to advise the Steering Committee on technical decisions, processes and survey content. Templates of generic ToRs for Steering and Technical Committees are provided by UNICEF RO/HQ.

**II. Technical Preparations for Data Collection**

1. **Questionnaire Design.** Draft questionnaires based on the standard MICS questionnaires are customised, shared with UNICEF RO and/or HQ for review. Once an agreement is reached among the parties on the questionnaires as a result of multiple reviews and feedback, questionnaires are drafted for the pre-test. During or towards the end of the review process, the questionnaires are translated into local language(s) and back translated to make sure that the standard MICS questionnaires and the local versions are fully compatible. The translation of the Manual for Mapping and Household Listing (described in II.4), interviewers, supervisors and measurers takes place at about the same time. Back translations are also reviewed by UNICEF RO and/or HQ.
2. **Sampling.** The survey sample is designed in the country. UNICEF RO organises a visit and/or online consultation of the regional sampling expert to discuss the key parameters of sampling design. The sample design document is drafted by the national sampling expert and reviewed by the regional sampling expert, who must have access to all the information on the sample frame. After the sampling design document is finalised, the first version of the sample weights calculation worksheet is produced in line with the MICS template and shared with UNICEF RO for review. The first-stage selection of the sample is made.
3. **Supplies.** Based on the content of the questionnaires and size of sample and according to the MICS Supply Procurement Instructions, the types and quantities of supplies needed for the survey are determined and discussed with UNICEF RO. Supplies are ordered by the country. Sufficient time should be allowed between the procurement time and the expected date of delivery of the items prior to the start of pre-test training and data collection.
4. **Listing Training and Listing.** Listing training is conducted for listers and mappers according to the recommendations described in the MICS Manual for Mapping and Household Listing. The agenda of the training as well as listing forms to be used are reviewed by the regional sampling expert and, when used, the data entry application is reviewed by the regional data processing expert. Based on the sample selection and according to the Manual for Mapping and Household Listing, the NSO conducts household listing and selection in sampled clusters. As needed, UNICEF RO sends the regional sampling expert and/or the regional data processing expert to support the training and/or the first days of listing. Household selection is also reviewed by the regional sampling expert, either remotely or while in the country. The second-stage selection of the sample is made.
5. **Pre-test of Questionnaires.** The questionnaires are pre-tested after appropriate training. The training agenda, which should be similar in content to the main training agenda, is reviewed by UNICEF RO in advance. The regional household survey expert supports the training and the pre-test. The pre-test report is developed and shared with UNICEF RO for review. Questionnaires are finalised after the agreement of parties. Sufficient time should be allowed between the questionnaire pre-test and the CAPI/data entry application pre-test to make sure that all the questionnaires can be carefully reviewed before the CAPI/data entry application is pre-tested.
6. **Second Workshop on Data Processing.** The country survey team including the national MICS data processing coordinator and national MICS consultant, participates in this workshop to strengthen skills in the utilisation of the two software packages used by MICS (CSPro and SPSS) and enhance understanding of MICS data processing methodology, protocols, standards and technical guidelines. The regional data processing expert participates in the workshop and supports the country team, together with the Global MICS data processing team, with adaptation of the data entry application and tabulation programmes (syntaxes). At the same workshop, the country survey team gets familiarised with customisation of survey archives. The technical coordinator of the National Statistic Office and the UNICEF MICS focal point also participate to this workshop.
7. **Data Entry Application.** During the MICS data processing Workshop, participants are trained in customising the MICS CAPI/data entry and editing application and tabulation programmes. The applications are fully customised and completed in the country, based on the pre-tested and final questionnaires and then sent to UNICEF RO/HQ for review and feedback. The CAPI/data entry application is then pre-tested and finalised. The pre-test is supported by the regional data processing expert.

**III. Fieldwork**

1. **Fieldwork Training and Pilot Study.** A 4-5-week field staff training is conducted in the country, including field practice and a pilot study. The regional household survey expert mobilised by UNICEF RO supports the training. The agenda of the training is shared in advance with UNICEF RO/HQ for review and feedback.
2. **Fieldwork/Data Collection.** The regional household survey expert as well as the UNICEF RO MICS Coordinator support monitoring of field work (in particular during the early stages). Field Check Tables are produced in the country and shared with UNICEF RO together with the interim data files for review and comments. Secondary editing happens simultaneously.

**IV. Analysis**

1. **Creating Analysis Files.** Data editing and cleaning is completed. Sample weights are finalised, reviewed by the regional sampling expert and appended to the micro data files. UNICEF RO mobilises the regional data processing expert to provide technical assistance in the country for finalisation of data editing and cleaning of databases, exporting files to SPSS as well as the finalisation of the customisation of the SPSS tabulation programmes. CSPro files, SPSS syntaxes used for preparing data for analysis and micro data files are shared with UNICEF RO/HQ for a remote review. Final micro data files are produced ready for tabulation.
2. **Data Analysis and Tabulation.** A complete set of survey result tables is produced. The SPSS tabulation programmes and tabulations prepared in line with the customised MICS tabulation plan format are shared with UNICEF RO for review. UNICEF RO mobilises the regional household survey expert to provide technical assistance as needed. The country survey team adapts tabulations and programmes based on feedback and shares with UNICEF HQ for consolidated review. Final tabulations including data quality and sampling errors tables are produced for the Survey Findings Report (SFR).
3. **Workshop** **on Data Interpretation, Further Analysis and Dissemination.** The country survey team participates in this workshop to enhance their skills and knowledge on interpretation of data and learn from each other’s experience and to review and discuss survey findings with global and regional experts. A draft SFR with all tables and annexes based on the MICS template is developed during the workshop. At the same workshop, country teams identify potential areas for further analysis, broaden their knowledge of various tools and methods for effective dissemination of MICS data and make progress on archiving work. MICS dissemination templates and examples are made available by UNICEF RO/HQ.

**V. Dissemination of Survey Results**

1. **Survey Findings Report.** Thedraft SFR developed at the third workshop is finalised in the country, and shared with UNICEF RO/HQ for review. The final SFR is shared in pdf version with UNICEF RO/HQ for global dissemination at [mics.unicef.org](http://mics.unicef.org/).
2. **Final Report Writing.** The Final Report (FR) is an optional dissemination product, which is recommended, but as of MICS6 no longer a required undertaking. UNICEF considers the Project completed satisfactory if the full SFR is disseminated within 6 months after the completion of data collection, together with the anonymised micro data files. If pursued, adraft of the FR is produced on the basis of MICS templates and shared with UNICEF RO for a review and feedback. RO mobilises the regional household survey expert to provide support in the country or remotely, as needed. The country survey team integrates RO comments and sends another version for UNICEF HQ review. The final FR is shared in pdf version with UNICEF RO/HQ for global dissemination at [mics.unicef.org](http://mics.unicef.org/).
3. **Printing (SFR and/or FR).** If a printed version is planned, the print-ready file of the report(s) is sent to UNICEF RO/HQ for feedback. A specified number of hard copies are shipped to UNICEF RO/HQ.
4. **Data Sharing.** With the support from UNICEF RO/HQ micro data files are anonymised in accordance with international standards, so that no individual, household or cluster location can be identified. A set of standard variables are added to the micro data files along with any necessary notes on using the data and contact information of the NSO. Micro data files are uploaded to [mics.unicef.org](http://mics.unicef.org/).
5. **Completion of Archiving.** The MICS survey archive is completed. UNICEF regional household survey and data processing experts review and provide feedback. The final archive is shared with UNICEF HQ for review and then finalised and uploaded to [mics.unicef.org](http://mics.unicef.org/).
6. **Dissemination and Further Analysis.** Dissemination materials are produced and further analysis of MICS data is planned in collaboration with partners. Support to production of dissemination materials and further analysis will be provided, on request, by UNICEF RO and HQ, as needed.