## Calculating Fieldwork Duration
Template for calculating the duration of fieldwork
Enter values from the MICS survey plan into the input value table. The corresponding estimates of fieldwork duration will be shown in the output value table.
INPUT VALUES |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of households (Total sample size) | 12500 | Total number of working days needed | 4166.6667
Number of households to be completed per day per interviewer1 (net) | 3 | Number of households completed per day per team | 12
Number of fieldwork teams2 | 15 | Number of households completed per day for all teams | 180
Number of interviewers per team3 | 4 | Duration of fieldwork in working days | 69.4444
Number of households per cluster4 | 20 | Total duration in weeks | 13.8889
1 week = 5 working days + 1 rest & 1 travel day
Fieldwork start date [dd/mm/yyyy] | 2013-09-01 | Fieldwork end date [dd/mm/yyyy] | 2013-12-07 05:20
1 On average interviewers should be able to comfortably complete up to 3-4 household per day, including all questionnaires. The number here is net, meaning that it includes re-visits to the households. Aiming for larger numbers of households per day will lead to problems in data quality.
2 The number of fieldwork teams needs to be kept to a manageable size (between 5-20 teams is recommended) in order to ensure field monitoring and quality assurance measures can be undertaken.
3 MICS recommends that field teams have 4 interviewers (1 supervisor, 1 editor and 1 measurer)
4 MICS recommends between 15 to 25 households per cluster
Formulas:
Value = [Value]+F14/5*7

## Calculating Fieldstaff Required
Template for calculating total number of teams and fieldwork staff required for fieldwork and training
Enter values from the MICS survey plan into the input value table (requires input on fieldwork duration and DP requirement spreadsheets). The corresponding estimates of fieldwork staff requirement and training participants will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Calculating Fieldwork Duration' |  | OUTPUT VALUES FOR FIELDWORK
Parameter | Value | Estimates | Value
Number of households | 12500 | Number of clusters | 625
|  | Duration of fieldwork in working days | 69.4444
Number of households per cluster | 20 | Number of total interviews per day | 180
Duration of fieldwork in weeks 1 week = 5 working days + 1 rest & 1 travel day | 13.8889 | Number of fieldwork teams required | 15
Number of visited households per day per interviewer | 3 | Number of Fieldwork staff Required:
|  | Supervisors | 15
Number of interviewers per team | 4 | Interviewers | 60
|  | Editors | 15
|  | Measurers | 15
INPUT VALUES |  | Total | 105
|  | Total + 10 % extra for selection of best performing/replacement | 115.5
Parameter | Value
OUTPUT VALUES FOR TRAINING
Data Entry Supervisor(s)6 | 1
|  | Estimates | Value
Secondary Editors6 | 2
|  | Supervisors | 15
Questionnaire Administrators6 | 2 | Interviewers | 60
|  | Editors | 15
|  | Measurers | 15
INPUT VALUES READ FROM THE WORKSHEET 'Calculating DP Requirement' |  | 10 % extra for selection of best performing/replacement | 10.5
|  | Data Entry Supervisor(s) | 1
Data Entry Operators6 | 14.1844 | Secondary Editors | 2
|  | Questionnaire Administrators | 2
|  | Data Entry Operators | 14.1844
5 Fieldwork teams require one off-day every week. Further, one (net) travel day per week is assumed based on a team typically covering a number of clusters from a changing base location, driving to and from clusters every day, and moving base approximately once a week. The number of travel days should be increased if team movement generally follow a different pattern, i.e. without such base locations. This would be the case if long distances between clusters. |  | 10 % extra for selection of best performing/replacement | 1.9184
|  | Total to train7 for fieldwork | 136.6028
7 Training facilities should include 1 large room for plenary sessions and smaller classrooms for smaller, interactive sessions, for 30-40 participants per room, if capacity and number of trainers allow for simultaneous sessions. More trainees per room can reduce quality of training.
6 MICS recommends that data entry personnel are also familiarized with questionnaires during the main fieldworker training. Data entry supervisors, Secondary Editors, Questionnaire Administrators, and, if possible, data entry operators should also be included in the total number for the main fieldwork training.
Note on E12: MICS: Calculated to check the consistency with the input from 'Calculating Fieldwork Duration' worksheet

## Calculating DP Requirement
Template for Calculating Data Processing Requirements
Enter values from the MICS survey plan and values from previous surveys into the input value table (requires input on fieldwork duration spreadsheet). The corresponding estimates of data processing requirements will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Calculating Fieldwork Duration' |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of households (Total sample size) | 12500 | Assumed work rate8 | 17.9775
(number of households per operator per day)
Fieldwork start date [dd/mm/yyyy] | 2013-09-01
|  | Number of days of data entry | 83.3333
Data entry start date (Fieldwork start + 2 weeks) [dd/mm/yyyy] | 2013-09-15
|  | Number of operators needed | 14.1844
Targeted end day of data entry (Fieldwork end date + 2 weeks) | 2013-12-21 05:20
|  | Number of computers needed | 15.1844
INPUT VALUES |  | 8 Normal assumption is that an operator on an 8 hour shift can enter 20 households with one woman, one man, and one child. Value here will change depending of composition of households.
Parameter | Value
Number of women (15-49) per household | 1.25
Number of men (15-49) per household | 1.09
Number of children (U5) per household | 1.11
Working days per week | 6
Shifts | 1
Hours per shift | 8
Note on B14: MICS: Can be modified, but should not be less than fieldwork end-date + 2 weeks.
Note on B21: MICS: Enter values from a previous survey or best estimate

## Calculating Supply Requirement
Template for calculating supply requirements
No value input required.
OUTPUT VALUES
Parameter | Value
Measuring Boards9 | 30
Scales9 | 30
Salt Test Kits10 | 506.6028
GPS Units9 | 30
OUTPUT VALUES READ FROM THE WORKSHEET 'Calculating DP Requirement'
Parameter | Value
Number of computers needed | 15.1844
9 Number of Measuring Boards, Scales, and GPS units are calculated as 2 per team (one back-up)
10 Number of Salt Test Kits is based on 50 households covered per kit, plus 2 extra per interviewer, and 1 per participant in fieldwork training. Add to cover pretest requirements.