## Fieldwork Duration
Template for calculating the duration of fieldwork
Enter values from the MICS survey plan into the input value table. The corresponding estimates of fieldwork duration will be shown in the output value table. This spreadsheet serves as input to the other sheets in the workbook. It is therefore advisable to first enter data here and later continuously confirm that the correct values are entered in inputs here.
INPUT VALUES |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of households (Total sample size) | 12500 | Total number of working days needed | 4166.6667
Number of households to be completed per day per interviewer1 (net) | 3 | Number of households completed per day per team | 12
Number of fieldwork teams2 | 15 | Number of households completed per day for all teams | 180
Number of interviewers per team3 | 4 | Duration of fieldwork in working days | 69.4444
|  | Total duration in working weeks | 13.8889
Number of households per cluster4 | 20 | 1 week = 5 working days + 1 rest & 1 travel day5
|  | Total duration of the fieldwork in days | 83.3333
Fieldwork start date [d-mmm-yyyy] | 2017-06-01
|  | Fieldwork end date [d-mmm-yyyy] | 2017-09-06 05:20
1 On average interviewers should be able to comfortably complete up to 3-4 household per day, including all questionnaires. The number here is net, meaning that it includes re-visits to the households. Aiming for larger numbers of households per day will lead to problems in data quality.
2 The number of fieldwork teams needs to be kept to a manageable size (between 5-20 teams are recommended) in order to ensure field monitoring and quality assurance measures can be undertaken.
3 MICS recommends that field teams have 4 interviewers, as well as 1 supervisor and 1 measurer. For PAPI surveys a field editor is also required on each team.
4 MICS recommends between 15 to 25 households per cluster
5 Fieldwork teams require one off-day every week. Further, one (net) travel day per week is assumed based on a team typically covering a number of clusters from a changing base location, driving to and from clusters every day, and moving base approximately once a week. The number of travel days should be increased if team movement generally follow a different pattern, i.e. without such base locations. This would be the case if long distances between clusters.
Formulas:
Value = [Value, row above]+(F14/5*7)

## Listing Duration
Template for calculating the duration of household listing and mapping
Enter values from the MICS survey plan into the input value table (requires input on 'Fieldwork Duration' spreadsheet). The corresponding estimates of listing and mapping duration will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration'
Number of clusters | 625
INPUT VALUES |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of clusters to be completed per working day per listing team6 | 1 | Total number of working days needed + 25%8 | 781.25
Number of listing teams7 | 15 | Duration of listing and mapping in working days | 52.0833
|  | Total duration in weeks | 8.6806
1 week = (6 working days + 1 rest)9
Listing and mapping start date [d-mmm-yyyy] | 2017-02-01 | Fieldwork end date [d-mmm-yyyy] | 2017-05-03 03:30
6 On average one lister and one mapper should be able to comfortably complete 1 cluster per day (generally with an overall average of 80 to 120 households each). It should be possible even if the survey additionally collects information on presence of children under age 5 in listed households (or similar needed for over-sampling), extra question on special populations such as Roma or if a lack of census maps or with old maps. More than one cluster per day is possible mainly in urban clusters and requires newly created maps or ortho-photos and more attention in listing.
7 The number of teams needs to be kept to a manageable number that can be adequately trained and monitored in the field. It is recommended to have a maximum of 3 teams per region and no more than 50 staff to manage.
8 Extra travel days should be considered for teams covering large geographic areas or remote clusters with lengthy or demanding travel involved (long drive, walking, sailing). Regardless, it is recommendedto keep these 25% additional days for any survey to account for large clusters, segmentation, bad weather conditions, re-visits, etc.
9 The Listing and Mapping teams require one off-day every week.
Formulas:
Value = [Value]+(F15/4*7)

## Listing Staff
Template for calculating number of staff required for household listing and mapping
Enter values from the MICS survey plan into the input value table (requires input on 'Fieldwork Duration' spreadsheet). The corresponding estimates of listing and mapping staff requirement and training participants will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Listing Duration' |  | OUTPUT VALUES FOR FIELDWORK
Parameter | Value | Estimates | Value
Number of clusters | 625 | Number of Fieldwork staff Required:
|  | Supervisors12 | 5
Number of listing teams | 15 | Listers | 15
|  | Mappers | 15
Duration in weeks | 8.6806 | Total | 35
1 week = 6 working days + 1 rest |  | Total + 10 %13 extra for selection of best performing/replacement | 39
INPUT VALUES |  | OUTPUT VALUES FOR TRAINING
Parameter | Value | Estimates | Value
Central office staff |  | Supervisors | 5
Listing Editors10 | 2 | Listers | 15
|  | Mappers | 15
Mapping Editors/Administrators11 | 2 | 10 %13 extra for selection of best performing/replacement | 4
|  | Listing Editors | 2
|  | Mapping Editors/Administrators | 2
10 The Listing Editors manage day-to-day edits on listing data received from the field and communicate findings with the survey management team. |  | Total to train14 for listing and mapping | 43
11 Similarly, the Mapping Editors or Administrators manage and compile maps received from the field. |  | 12 A Supervisor is expected to supervise the work of 3 teams.
13 Depending on experience with drop-outs and capacity, the number of extra trainees can be increased, but should not be reduced.
14 Training facilities should include 1 large room for plenary sessions and 2 smaller classrooms for split sessions for listers and mappers.

## Fieldwork Staff
Template for calculating total number of teams and fieldwork staff required for fieldwork and training
Enter values from the MICS survey plan into the input value table (requires input on fieldwork duration). The corresponding estimates of fieldwork staff requirement and training participants will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration' |  | OUTPUT VALUES FOR FIELDWORK
Parameter | Value | Estimates | Value
Number of households | 12500 | Number of clusters | 625
|  | Duration of fieldwork in working days | 69.4444
Number of households per cluster | 20 | Number of total interviews per day | 180
|  | Total duration of the fieldwork in days (output from 'Fieldwork Duration') | 83.3333
Duration of fieldwork in weeks 1 week = 5 working days + 1 rest & 1 travel day15 | 13.8889 | Number of fieldwork teams required (Calculated to check the consistency with the input from 'Calculating Fieldwork Duration' worksheet) | 15
Number of visited households per day per interviewer | 3 | Number of Fieldwork staff Required:
|  | Supervisors | 15
Number of interviewers per team | 4 | Interviewers | 60
|  | Measurers | 15
|  | Total | 90
INPUT VALUES |  | Total + 10 % extra for selection of best performing/replacement | 99
Parameter | Value | OUTPUT VALUES FOR TRAINING
Central office staff |  | Estimates | Value
Secondary Editors16 | 2
|  | Supervisors | 15
|  | Interviewers | 60
15 Fieldwork teams require one off-day every week. Further, one (net) travel day per week is assumed based on a team typically covering a number of clusters from a changing base location, driving to and from clusters every day, and moving base approximately once a week. The number of travel days should be increased if team movement generally follows a different pattern, i.e. without such base locations. This would be the case if long distances between clusters. |  | Measurers | 15
|  | 10 % extra for selection of best performing/replacement | 9
|  | Secondary Editors | 2
|  | Total to train17 for fieldwork | 101
16 MICS recommends that data processing personnel are also familiarized with questionnaires during the main fieldworker training. Secondary Editors should also be included in the total number for the main fieldwork training. |  | 17 Training facilities should include 1 large room for plenary sessions and smaller classrooms for smaller, interactive sessions, for 30-40 participants per room, if capacity and number of trainers allow for simultaneous sessions. More trainees per room can reduce quality of training.

## Supplies
Template for calculating supply requirements
No value input required.
OUTPUT VALUES
Parameter | Value
Measuring Boards18 | 30
Scales18 | 30
Salt Test Kits19 | 471
Tablet Computers20 - see additional sheet | 95
Water Quality Testing Equipment 21 - See additional sheet | 17
18 Number of Measuring Boards and Scales are calculated as 2 per team (one back-up). The number of back-ups can be reduced if teams have easy access to replacements from a central location. Hand sanitiser and a mild cleaning agent is also recommended for use for anthropometric measurements and equipment.
19 Number of Salt Test Kits is based on 50 households covered per kit, plus 2 extra per interviewer, and 1 per participant in fieldwork training. Add to cover pretest requirements. If salt has alkaline, a second test is often needed. Check this from previous surveys and subject matter experts, as more kits may be needed. If necessary to test salt for both iodate and iodide, additional test kits need to be added. This template only accounts for one type of test.
20 One tablet per supervisor and interviewer plus one additional per team. An (additional) extra tablet per team is recommended if number of interviewers per team is higher than 4. The number includes 5 additional tablets for survey managers and monitoring staff. If GPS readings are included in the survey, investigate if tablets can do GPS readings adequately to capture cluster location. If not, each team should be equipped with two GPS units.
21 Each team should be equipped with one water quality testing bag with hardware items specified in protocol. The number of bags here includes an additional 10% as recommended. Teams should carry enough consumables and additional items to perform their assigned number of samples, including an additional 25%.

## Tablet Supplies
Template for calculating tablet accessories
No value input required.
OUTPUT VALUES
Parameter | Value
Tablet Computers | 95
Tablet Cases | 95
Tablet screen protectors | 95
SD Cards | 95
Back-up power supplies/Power Banks22 | 30
Styluses23 | 125
Vehicle Charger24 | 15
22 Two back-up power supplies per team - one should be able to fully charge two tablets
23 One stylus per tablet + two additional per team. Note that some tablets include stylus.
24 One vehicle charger per team

## Water Quality Supplies
Template for calculating water quality testing supply requirements
Enter values from the MICS survey plan into the input value table (requires additional input on 'Fieldwork Duration' spreadsheet). Also confirm values in red in the output value table. The corresponding estimates of supplies needed for water quality testing will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration' |  | OUTPUT VALUES
Parameter | Value | Parameter | Total Units | Units per Team | Cost/pack26 | Units/pack | Packs needed | Total Cost
Number of clusters | 625 | Hardware
- an additional 10% is added to Total Units for replacement needs
Number of fieldwork teams | 15 | Manifolds | 17 | 1 | 887.8 | 1 | 17 | 15092.6
|  | Incubation belts | 33 | 2 | 30.57 | 1 | 33 | 1008.81
|  | Syringes, 100 mL | 33 | 2 | 93.11 | 50 | 1 | 93.11
INPUT VALUES |  | Forceps | 33 | 2 | 21.86 | 1 | 33 | 721.38
|  | Hardware sub-total | [5 empty] | 16915.9
Parameter | Value
Consumables
Number of household water quality samples per cluster | 5 | - an additional 25% is added to Total Units for training and wastage
|  | Funnel and membrane | 8594 | 459 | 143.23 | 150 | 58 | 8307.34
Number of source water quality samples per cluster | 5 | CompactDry plate | 8594 | 459 | 1484.6235 | 1404 | 7 | 10392.3648
|  | Disposable syringes, 1 mL | 8594 | 459 | 12.2 | 120 | 72 | 878.4
Number of blank tests per cluster | 1 | Alcohol wipes | 8594 | 459 | 8.43 | 100 | 86 | 724.98
|  | Sample collection bags | 7813 | 417 | 61.51 | 500 | 16 | 984.16
|  | Chlorine tablets 8.5 mg | 8594 | 459 | 0.43 | 100 | 86 | 36.98
|  | Consumables sub-total | [5 empty] | 21324.2248
|  | Freight (10%) | [5 empty] | 3824.0125
|  | Additional Items25 | [5 empty] | 1700
|  | 25 A dedicated water testing bag per team is needed for the water testing equipment and it is advisable to also procure a large bag for storing consumables in the vehicle. Bottled water known to be of high quality, for example distilled water or a reliable brand of mineral water is needed for the "blank test". Additional items required for water quality testing are: hand sanitiser, trash bags, permanent marker pens. Paper towels are also recommended to clean any spills. The total cost of these items are here estimated at USD 100 per kit, but change if estimates differ. |  |  |  |  | Total (USD): | 43764.1373
26 Please note that the cost/pack values should be updated for a better estimate. With fluctuations in EUR/USD rates there are bound to be significant changes. The current price is available from the UNICEF Supply catalogue, using item numbers provided in the MICS6 Supply Procurement Instructions, available here: http://mics.unicef.org/tools#survey-design