## Fieldwork Duration
Template for calculating the duration of fieldwork
Enter values from the MICS survey plan into the input value table. The corresponding estimates of fieldwork duration will be shown in the output value table. This spreadsheet serves as input to the other sheets in the workbook. It is therefore advisable to first enter data here and later continuously confirm that the correct values are entered in inputs here.
INPUT VALUES |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of households (Total sample size) | 12000 | Total number of working days needed | 4000
Number of households to be completed per day per interviewer1 (net) | 3 | Number of households completed per day per team | 12
Number of fieldwork teams2 | 20 | Number of households completed per day for all teams | 240
Number of interviewers per team3 | 4 | Number of working days per cluster (rounded) | 2
Number of households per cluster4 | 20 | Duration of fieldwork in working days | 50
|  | Total duration in working weeks | 10
1 week = 5 working days + 1 rest & 1 travel day5
|  | Total duration of the fieldwork in days | 70
Fieldwork start date [dd-mm-yyyy] | 2023-08-01 | Fieldwork end date [dd-mm-yyyy] | 2023-10-10
1 On average interviewers should be able to comfortably complete up to 3-4 household per day, including all questionnaires. The number here is net, meaning that it includes re-visits to the households. Aiming for larger numbers of households per day will lead to problems in data quality.
2 The number of fieldwork teams needs to be kept to a manageable size (between 5-20 teams are recommended) in order to ensure field monitoring and quality assurance measures can be undertaken.
3 MICS recommends that field teams have 4 interviewers, as well as 1 supervisor and 1 measurer.
4 MICS recommends between 15 to 25 households per cluster
5 Fieldwork teams require one off-day every week. Further, one (net) travel day per week is assumed based on a team typically covering a number of clusters from a changing base location, driving to and from clusters every day, and moving base approximately once a week. The number of travel days should be increased if team movement generally follow a different pattern, i.e. without such base locations. This would be the case if long distances between clusters.
Formulas:
Value = [Value]+(F16/5*7)

## Fieldwork Staff
Template for calculating total number of teams and fieldwork staff required for fieldwork and training
Enter values from the MICS survey plan into the input value table (requires input on fieldwork duration). The corresponding estimates of fieldwork staff requirement and training participants will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration' |  | OUTPUT VALUES FOR FIELDWORK
Parameter | Value | Estimates | Value
Number of households | 12000 | Number of clusters | 600
|  | Duration of fieldwork in working days | 50
Number of households per cluster | 20 | Number of total interviewed households per day | 240
|  | Total duration of the fieldwork in days (output from 'Fieldwork Duration') | 70
Duration of fieldwork in weeks 1 week = 5 working days + 1 rest & 1 travel day6 | 10 | Number of fieldwork teams required (Calculated to check the consistency with the input from 'Calculating Fieldwork Duration' worksheet) | 20
Number of interviewed households per day per interviewer | 3 | Number of Fieldwork staff Required:
|  | Supervisors | 20
Number of interviewers per team | 4 | Interviewers | 80
|  | Measurers | 20
|  | Total | 120
INPUT VALUES |  | Total + 10 % extra for selection of best performing/replacement | 132
Parameter | Value | OUTPUT VALUES FOR TRAINING
Central office staff |  | Estimates | Value
Secondary Editors7 | 1 | Supervisors | 20
|  | Interviewers | 80
Monitoring staff8 | 6 | Measurers | 20
|  | 10% extra for selection of best performing/replacement | 12
|  | Secondary Editors | 1
|  | Monitoring staff | 6
6 Fieldwork teams require one off-day every week. Further, one (net) travel day per week is assumed based on a team typically covering a number of clusters from a changing base location, driving to and from clusters every day, and moving base approximately once a week. The number of travel days should be increased if team movement generally follows a different pattern, i.e. without such base locations. This would be the case if long distances between clusters. |  | Total to train9 for fieldwork | 139
9 Training facilities should include 1 large room for plenary sessions and smaller classrooms for smaller, interactive sessions, for 30-40 participants per room, if capacity and the number of trainers allow for simultaneous sessions. More trainees per room can reduce the quality of training. A separate space should be planned for anthropometry measurers training, taking into account the space needed for equipment and number of measures.
7 MICS recommends that data processing personnel are also familiarized with questionnaires during the main fieldworker training. Secondary Editors should also be included in the total number for the main fieldwork training.
8 The composition of the monitoring team(s) should be decided at the planning stage of the survey. The team members who do not belong to the NSO/UNICEF MICS team must attend the first part of the training (methodology part, and preferably the whole training). A separate session should be organized for monitoring teams.

## Listing Duration
Template for calculating the duration of household listing and mapping
Enter values from the MICS survey plan into the input value table (requires input on 'Fieldwork Duration' spreadsheet). The corresponding estimates of listing and mapping duration will be shown in the output value table. Discuss details with the sampling expert.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration'
Number of clusters | 600
INPUT VALUES |  | OUTPUT VALUES
Parameter | Value | Estimates | Value
Number of clusters to be completed per working day per listing team10 | 1 | Total number of working days needed + 20%12 | 720
Number of listing teams11 | 15 | Duration of listing and mapping in working days | 48
|  | Total duration in weeks | 8
1 week = (6 working days + 1 rest)13
Listing and mapping start date [dd-mm-yyyy] | 2022-02-01 | Fieldwork end date [dd-mm-yyyy] | 2022-03-29
10 On average one lister and one mapper should be able to comfortably complete 1 cluster per day (generally with an overall average of 80 to 120 households each). It should be possible even if the survey additionally collects information on presence of children under age 5 in listed households (or similar needed for over-sampling), extra question on special populations such as Roma or if a lack of census maps or with old maps. More than one cluster per day is possible mainly in urban clusters and requires newly created maps or ortho-photos and more attention in listing.
11 The number of teams needs to be kept to a manageable number that can be adequately trained and monitored in the field. It is recommended to have a maximum of 3 teams per region and no more than 50 staff to manage.
12 Extra travel days should be considered for teams covering large geographic areas or remote clusters with lengthy or demanding travel involved (long drive, walking, sailing). Regardless, it is recommended to keep a minimum 20% additional days for any survey to account for large clusters, segmentation, bad weather conditions, re-visits, etc. This should be discused with samoling expert when planning fro listing and mapping data collection
13 The Listing and Mapping teams require one off-day every week.
Formulas:
Value = [Value]+(F15/6*7)

## Listing Staff
Template for calculating number of staff required for household listing and mapping
Enter values from the MICS survey plan into the input value table (requires input on 'Fieldwork Duration' spreadsheet). The corresponding estimates of listing and mapping staff requirement and training participants will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Listing Duration' |  | OUTPUT VALUES FOR FIELDWORK
Parameter | Value | Estimates | Value
Number of clusters | 600 | Number of Fieldwork staff Required:
|  | Supervisors16 | 5
Number of listing teams | 15 | Listers | 15
|  | Mappers | 15
Duration in weeks | 8 | Total | 35
1 week = 6 working days + 1 rest |  | Total + 10%17 extra for selection of best performing/replacement | 39
INPUT VALUES |  | OUTPUT VALUES FOR TRAINING
Parameter | Value | Estimates | Value
Central office staff |  | Supervisors | 5
Listing Editors14 | 1 | Listers | 15
|  | Mappers | 15
Mapping Editors/Administrators15 | 2 | 10 %17 extra for selection of best performing/replacement | 4
|  | Listing Editors | 1
|  | Mapping Editors/Administrators | 2
14 The Listing Editors manage day-to-day edits on listing data received from the field and communicate findings with the survey management team. |  | Total to train18 for listing and mapping | 42
15 Similarly, the Mapping Editors or Administrators manage and compile maps received from the field. |  | 16 A Supervisor is expected to supervise the work of 3 teams.
17 Depending on experience with drop-outs and capacity, the number of extra trainees can be increased but should not be reduced.
18 Training facilities should include 1 large room for plenary sessions and 2 smaller classrooms for split sessions for listers and mappers.

## Supplies
Template for calculating supply requirements
No value input required.
OUTPUT VALUES |  | OUTPUT VALUES - Optional supplies
Parameter | Value | Parameter | Value
Measuring Boards19 | 40 | Tablet Computers for listing22 - see additional sheet | 17
Scales19 | 40 | GPS units - See additional sheet | 17
Tablet Computers20 - see additional sheet | 125
22 One tablet per lister. The number includes 10% of the total number of tablets for backup. In case CAPI listing is used. Depending on the planning of the listing and the main training start date, there is no need for additional equipment for the listing.
Water Quality Testing Equipment21 - See additional sheet | 22
19 Numbers of Measuring Boards and Scales are calculated as 2 per team (one back-up). The number of back-ups can be reduced if teams have easy access to replacements from a central location. Hand sanitiser (at least 10 bottles per team) and a mild cleaning agent (quantity can be calculated when the total number of children for measurement is estimated) are also recommended for use for anthropometric measurements and equipment.
20 One tablet per supervisor and interviewer plus one additional per team. An (additional) extra tablet per team is recommended if number of interviewers per team is higher than 4. The number includes 5 additional tablets for survey managers and monitoring staff.
21 Please see detailes in separate sheet.

## Tablet Supplies Main
Template for calculating tablet accessories for the main data collection
No value input required.
OUTPUT VALUES
Parameter | Value
Tablet Computers | 125
Tablet Cases | 125
Tablet screen protectors | 125
SD Cards | 125
Back-up power supplies/Power Banks23 | 40
Styluses24 | 165
Vehicle Charger25 | 20
23 Two back-up power supplies per team - one should be able to fully charge two tablets
24 One stylus per tablet + two additional per team. Note that some tablets include stylus.
25 One vehicle charger per team

## Optional supplies
Template for calculating supplies for optional topics
No value input required
OUTPUT VALUES CAPI Listing26 |  | OUTPUT VALUES GIS
Parameter | Value | Parameter | Value
Tablet Computers | 17 | GPS receiver (Garming device)30 | 17
(1 per team + two (2) extra for backup)
Tablet Cases | 17
|  | Pack of eight (8) AA batteries (alkaline) per GPS unit | 17
Tablet screen protectors | 17
|  | One (1) standard USB to Micro-USB cable per GPS unit for downloading data from receivers31 | 17
SD Cards | 17
|  | One (1) MicroSD card per GPS unit (optional) | 17
Back-up power supplies/Power Banks27 | 15
30 Validation of existing GPS data may be possible without stand-alone units.For different options and guidance, please see MICS7 Supply Procurement Instructions, available here: http://mics.unicef.org/tools#survey-design
Styluses28 | 45
Vehicle Charger29 | 15 | 31 Usually a cable is provided with the GPS receiver
26 In case CAPI listing is used. Depending on the planning of the listing and the main training start date, there is no need for additional equipment for the listing. One tablet per lister should be planned. The number includes 10% of the total number of tablets for backup. For countries where digital maps will be used, discuss supply needs with the data processing team.
27 One back-up power supply per team - should be able to fully charge two tablets
28 One stylus per tablet + two additional per team. Note that some tablets include stylus.
29 One vehicle charger per team

## Water Quality Supplies
Template for calculating water quality testing supply requirements
Enter values from the MICS survey plan into the input value table (requires additional input on 'Fieldwork Duration' spreadsheet). Also confirm values in red in the output value table. The corresponding estimates of supplies needed for water quality testing will be shown in the output value table.
INPUT VALUES READ FROM THE WORKSHEET 'Fieldwork Duration' |  | OUTPUT VALUES
Parameter | Value | Parameter | Total Units | Units per Team | Cost/pack32 | Units/pack |  | Packs needed | Total Cost
Number of clusters | 600 | Hardware
- an additional 10% is added to Total Units for replacement needs
Number of fieldwork teams | 20 | Membrane filtration manifold | 22 | 1.1 | 1120 | 1 | each | 22 | 24640
|  | Incubation belts | 22 | 1.1 | 4.2 | 1 | each | 22 | 92.4
|  | Syringes, 100 mL | 22 | 1.1 | 37.79 | 50 | per box | 1 | 37.79
INPUT VALUES |  | Metal forceps | 22 | 1.1 | 24.43 | 1 | each | 22 | 537.46
|  | Hardware sub-total | [6 empty] | 25307.65
Parameter | Value
Consumables
Number of household water quality samples per cluster | 5 | - an additional 25% is added to Total Units for training and wastage
|  | Millipore filter and cup | 8250 | 412.5 | 195.1 | 150 | per box | 55 | 10730.5
Number of source water quality samples per cluster | 5 | Nissui compact dry ECO plates | 8250 | 412.5 | 1562.5 | 1404 | per box | 6 | 9375
|  | Disposable sterile syringe (1 mL) | 8250 | 412.5 | 6.81 | 100 | per box | 83 | 565.23
Number of blank tests per cluster | 1 | Alcohol swabs | 8250 | 412.5 | 8.09 | 100 | per box | 83 | 671.47
|  | WhirlPak sample collection bags | 7500 | 375 | 80.85 | 500 | per box | 15 | 1212.75
|  | Chlorine tablets 8.5 mg | 8250 | 412.5 | 0.88 | 100 | per box | 83 | 73.04
|  | Consumables sub-total | [6 empty] | 22627.99
Parameter | Value
|  | Freight (10%) | [6 empty] | 4793.564
Additional or hardware | 10%
Additional for consumables | 25%
(contact WASH if planning adicional ToT) |  | 32 Please note that the cost/pack values should be updated for a better estimate. With fluctuations in EUR/USD rates there are bound to be significant changes. The current price is available from the UNICEF Supply catalogue, using item numbers provided in the MICS7 Supply Procurement Instructions, available here: http://mics.unicef.org/tools#survey-design | [5 empty] | Total (USD): | 52729.204
Additional for additional items | 10%
OUTPUT VALUES
|  | Parameter | Total Units | Units per Team | Cost/pack33 | Units/pack |  | Packs needed | Total Cost
Additional items
- an additional 10% is added to Total Units for training and wastage
|  | Hand sanitizer (5/team) | 110 | 5.5 | 3.18 | 1 | 250 ml bottle | 110 | 349.8
|  | Trash bags (1/cluster) | 750 | 37.5 | 2.16 | 30 | roll | 25 | 54
|  | Permanent marker (3/team) | 66 | 3.3 | 28.57 | 10 | packet | 7 | 199.99
|  | Water Quality Testing bag (1/team) | 22 | 1.1 | 2.96 | 1 | bag | 22 | 65.12
|  | Kitchen paper towel (12/team) | 264 | 13.2 | 7.27 | 1 | Roll of 100 | 264 | 1919.28
|  | Bottled Water for the blank tests (1/cluster) | 660 | 33 | 3 | 1 | 250 ml bottle | 660 | 1980
|  | Bags to store the materials in the vehicle (2/team) | 44 | 2.2 | 2.66 | 1 | bag | 44 | 117.04
|  | Ziploc bags (5/team) | 110 | 5.5 | 9.2 | 10 | packet | 11 | 101.2
|  | Additional items sub-total | [6 empty] | 4786.43
|  | Freight (10%) | [6 empty] | 478.643
|  | 33 Please note that the cost/pack values should be updated for a better estimate. With fluctuations in EUR/USD rates, there are bound to be significant changes. Most of the additional items are procured locally, while UNICEF branded bags (Water Quality testing bags and bags to store the materials) can be used and obtained from Supply Division as necessary. It is usually possible to use standard bags used by field teams for the water testing equipment. | [5 empty] | Total (USD): | 5265.073
|  | GRAND TOTAL | [5 empty] | Total (USD): | 57994.277